## Sheet1
Sr No | TASKS | Assigned to | Assisted by | Deadline | Status
1 | Project Idea brain-storming | Adarsh |  | 2017-04-07 | Done
Akhil
Ankit
Divya
Amulya
Sandesh
Nithya
2 | Developing Questionnaire | Akhil |  | 2017-04-11 | Done
Sandesh
3 | Conduct Interviews | Adarsh |  | 2017-04-24 | In-Progress
Akhil
Sandesh
4 | Conduct Interviews | Adarsh |  | 2017-04-25 | Done
Akhil
Sandesh
5 | Personas | Amulya |  | 2017-04-25 | Done
6 | Evaluation of interviews | Adarsh |  | 2017-04-26 | Done
Akhil
Sandesh
7 | MoSCoW Analysis | Sandesh |  | 2017-04-28 | Done
16 | User stories (not used) | Amulya | Adarsh | 2017-05-01 | Done
|  | Akhil | Ankit
|  | Sandesh | Nithya
8 | User Story 1 | Amulya |  | 2017-05-02 | Done
9 | User Story 2 | Amulya |  | 2017-05-02 | Done
10 | User Story 3 | Amulya |  | 2017-05-02 | Done
11 | User Story 4 | Amulya |  | 2017-05-02 | Done
12 | User Story 5 | Amulya |  | 2017-05-02 | Done
13 | User Story 6 | Amulya |  | 2017-05-02 | Done
14 | User Story 7 | Amulya |  | 2017-05-02 | Done
15 | Story Boarding | Amulya |  | 2017-05-02 | Done
17 | Low-fi prototype 1 | Adarsh |  | 2017-05-03 | Done
Akhil
Sandesh
18 | Low-fi prototype 2 | Amulya | Nithya | 2017-05-04 | Done
19 | Documentation | Akhil | Sandesh | 2017-05-04 | In-Progress
Adarsh
20 | Hifi Prototype 1 | Divya |  | 2017-05-04 | In-Progress
Ankit
21 | Hi-fi Prototype 1 | Divya |  | 2017-05-05 | Done
Ankit
22 | Testing 1 | Sandesh |  | 2017-05-05 | Done
23 | Hifi Prototype 2 | Divya |  | 2017-05-06 | In-Progress
Ankit
24 | Hi-fi Prototype 2 | Divya |  | 2017-05-07 | Done
Ankit
25 | Testing 2 | Sandesh |  | 2017-05-07 | Done
26 | Hifi-Prototype final | Divya |  | 2017-05-08 | Done
Ankit
27 | User experience map 1 | Nithya |  | 2017-05-09 | Done
28 | User experience map final | Adarsh |  | 2017-05-09 | Done
29 | Final Documentation | Akhil |  | 2017-05-10 | In-Progress
Adarsh
30 | Final Documentation | Akhil | Sandesh | 2017-05-11 | Done
Adarsh